## Sheet1
Task | Time(hours)
Angular basic theme setup, html integration with multilingual for all pages, lazy loading | 60
Login (multilingual) | 6
Forgot password | 4
Sidebar listing, folder/board option with functionality (rename, delete, create board, move board,move to folder) | 30
create boad/folder popup functionality in popup | 5
Dashboard, messages, load more feature, reply,task options(bookmark,copy link to update, mark as closed), Recent activities, Like feature, view likes | 32
Notification in header + profile dropdown options | 5
My profile (profile form, change password, Image uploading feature with cropping feature) | 8
Board page setup | 6
Board:- add new group | 4
Board:-edit group title, remove group,collapse group, colors | 5
Boards:- People | 5
Board:- status | 5
Board:- add new row | 3
Board(add new row):- title edit | 1
Board:- add new column | 10
Board(add new column):- Text, Tags, Numbers, Timeline, Date | 24
Who is on board popup+ team searching in popup | 5
Show activities | 2
Search in board | 3
Task Update Sidebar,Write an update, update listing, update options(pin to top, edit, delete), manage task subscribers | 16
Manage Team members listing+ Search name+ department listing | 8
Invite Team | 2
signup form for invited users | 3
Messaging | 24
Archive Board | 20
Recycle Bin | 20
Search in header | 3
Total expected hours | 319
319